## manti_by_20130531_1352
# | Id | Story | Labels | Iteration | Iteration Start | Iteration End | Story Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | Owned By | Description | URL | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Comment | Task | Task Status | Task | Task Status | Task | Task Status | Task | Task Status | Task | Task Status
1 | 43636107 | Create development and production branches | dev, git | 1 | 2013-01-28 | 2013-02-03 | feature | 3 | accepted | 2013-02-01 | 2013-02-01 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43636107
2 | 43634275 | Fix flip for teaser and description while edit post | blog, dev | 2 | 2013-02-04 | 2013-02-10 | bug |  | accepted | 2013-02-01 | 2013-02-08 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43634275 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/bdf97d94c34d6ca200b304bc1812fec0ec5195c8 [#43634275] Prevent flip for teaser and description (Manti - Feb 1, 2013)
3 | 43634625 | Fix success onSave popup message while edit post | blog, dev, popup | 2 | 2013-02-04 | 2013-02-10 | bug |  | accepted | 2013-02-01 | 2013-02-08 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43634625 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/3000bb4b9bc80cce0ff708cb15be3fa88aa327a6 [##43634625] Fix success onSave popup message while edit post (Manti - Feb 1, 2013)
4 | 43635349 | Fix multiple saving for new posts | blog, dev | 2 | 2013-02-04 | 2013-02-10 | bug |  | accepted | 2013-02-01 | 2013-02-08 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43635349 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/61315122cfac1c3df10a2aa005e6702932f0e5b3 [#43635349] Fix multiple saving for new posts, fix mysqli last returned result (Manti - Feb 1, 2013)
5 | 43634465 | Fix autocomplete with empty result set | autocomplete, dev | 2 | 2013-02-04 | 2013-02-10 | bug |  | accepted | 2013-02-01 | 2013-02-08 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43634465 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/d3a42fa7fde6bc1a5197f7699e70e5ce08f7d6d0 [#43634465] Fix autocomplete with empty result set (Manti - Feb 1, 2013)
6 | 43634713 | Fix file control population | controls, dev | 2 | 2013-02-04 | 2013-02-10 | bug |  | accepted | 2013-02-01 | 2013-02-08 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43634713 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/2c7eea98aaabb01772c59c36acf1c5a2d9c38b9b [#43634713] Fix file control population (Manti - Feb 6, 2013)
7 | 43634517 | Fix autocomplete add action | autocomplete, dev, markup | 2 | 2013-02-04 | 2013-02-10 | bug |  | accepted | 2013-02-01 | 2013-02-08 |  | Manti | Manti | Clear input field after add new tag | http://www.pivotaltracker.com/story/show/43634517 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/f03425112518af571a86ed63ca0d3c91fdd892d8 [#43634517] Clear input field after add new tag (Manti - Feb 1, 2013) | Fix markup for input overhead (Manti - Feb 4, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/c3de8ed287f8c2b2bfa37ff214ef42c8350c3c4f [#43634517] Fix control autosize (Manti - Feb 4, 2013)
8 | 43763497 | Fix autohide when click on popup | dev, popup | 2 | 2013-02-04 | 2013-02-10 | bug |  | accepted | 2013-02-04 | 2013-02-08 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43763497 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/1a3c63c0375c4700b140f2fe1682709903008ff6 [#43763497] Fix popup autohide (Manti - Feb 6, 2013)
9 | 43649507 | Add alias field to post edit form | blog, dev, sef | 2 | 2013-02-04 | 2013-02-10 | bug |  | accepted | 2013-02-01 | 2013-02-08 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43649507 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/0ac82b492a919b4547bd9e2850122a389ba2768c [#43649507] Add alias field to post edit form (Manti - Feb 6, 2013)
10 | 43599399 | Check popular counters | core, dev | 2 | 2013-02-04 | 2013-02-10 | feature | 2 | accepted | 2013-01-31 | 2013-02-08 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43599399 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/a4dce7411872c1dd59b1208bfb64c83c07b71333 [#43599399] Add viewed counter to sql queries (Manti - Feb 6, 2013)
11 | 43599317 | Popular front block | dev, markup | 2 | 2013-02-04 | 2013-02-10 | feature | 1 | accepted | 2013-01-31 | 2013-02-08 |  | Manti | Manti | Create popular front block | http://www.pivotaltracker.com/story/show/43599317 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/731040c709bb5ed3eb61c950620bf214c855812d [#43599317] Add popular front block (Manti - Feb 6, 2013)
12 | 43601655 | Add frontpage blog posts block | dev, front | 7 | 2013-03-11 | 2013-03-17 | feature | 2 | accepted | 2013-01-31 | 2013-03-11 |  | Manti | Manti | Add frontpage blog posts block which don't contains any items from "Featured" and "Popular" blocks. Also need ajax loading with the same behaviour. | http://www.pivotaltracker.com/story/show/43601655 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/7f63c8c91d3368dec21040e0527d6bd622d35308 [#43601655] Fix frontpage blog posts block (Manti - Feb 11, 2013)
13 | 43635369 | Add full gallery view | dev, gallery, markup | 7 | 2013-03-11 | 2013-03-17 | feature | 1 | accepted | 2013-02-01 | 2013-03-11 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43635369 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/49619201eeb5f24e16ad74fe7641272ee33b691d [#43635369] Fix missing request (Manti - Feb 10, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/02571da1ef2c3b42b06f86f33201440c743544b4 [#43635369] Fix output for gallery list (Manti - Feb 10, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/a92de16665f0b2fce78ceca609f33d0b8d7d4dbe [#43635369] Add full gallery view (Manti - Feb 11, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/6ea1df84343937f509f0d7a51cadb6c371b55746 [#43635369] Fix migration (Manti - Feb 15, 2013)
14 | 44191237 | Fix delete action for blog posts | blog, dev | 7 | 2013-03-11 | 2013-03-17 | bug |  | accepted | 2013-02-11 | 2013-03-11 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/44191237 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/fc771856ab1d0330d5fe1cb6ef6adf7ae8257c51 [#44191237] Add delete action fro blog posts (Manti - Feb 11, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/2f8c77a4b023303d25be1923d923ac79b17dbab2 [#44191237] Add callback for ajax loader (Manti - Feb 11, 2013)
15 | 43635393 | Add prev and next controls for gallery popup | dev, gallery, markup | 7 | 2013-03-11 | 2013-03-17 | feature | 1 | accepted | 2013-02-01 | 2013-03-11 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43635393 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/c07ac8eda5be98ddfd48e63c42b26632ae889d12 [#43635393] Add linkage to gallery files as in blog (Manti - Feb 12, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/19f22c1cf920b9742dcc2354532595e2a86cd4d9 [#43635393] Create new lin behaviour for gallery images (Manti - Feb 12, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/372d72f92b8435b3dbe8fde671f2527123d53731 [#43635393] Add MVC prev/next actions (Manti - Feb 12, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/5c8bb1223e1dd9a1f6822ab0694a3a4b396d57af [#43635393] Fix click for next and prev actions (Manti - Feb 13, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/321c0ec31128303b8a76a45cb5f7fabe6bbd1534 [#43635393] Add cycle show for gallery images (Manti - Feb 13, 2013)
16 | 43638255 | Fix autosize for html contents in popup | dev, markup, popup | 7 | 2013-03-11 | 2013-03-17 | bug |  | accepted | 2013-02-01 | 2013-03-11 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43638255 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/29329eaa77e23ea85c7cceadf61df7e47c945d8c [#43638255] Remove autosize, move image functionality to separate popup (Manti - Feb 27, 2013)
17 | 45141393 | Fix file form submit | dev, files | 7 | 2013-03-11 | 2013-03-17 | bug |  | accepted | 2013-02-26 | 2013-03-11 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/45141393 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/8f6ebaefba8e60e7ee3c691f8c6bfc296f5096f4 [#45141393] Add ajax loading for forms (Manti - Feb 27, 2013)
18 | 45219021 | Add separate image popup block | dev, images | 7 | 2013-03-11 | 2013-03-17 | feature | 1 | accepted | 2013-02-27 | 2013-03-11 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/45219021 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/b7faee9bf48975e237d153d3d83f1a3013dad4f4 [#45219021] Add separate image popup block (Manti - Feb 27, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/2cd495af7e5bd84ea58b1939a7e44e1dc063d42c [#45219021] Add popup icons (Manti - Feb 27, 2013)
19 | 43636069 | Add image resize with crop function | core, dev, images, resize | 7 | 2013-03-11 | 2013-03-17 | feature | 1 | accepted | 2013-02-01 | 2013-03-11 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43636069 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/382693223d21d4335a0ba9fed39e4cb0f61db905 [#43636069] Add resize with crop function (Manti - Feb 27, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/71e359ea14626c694aa42393c6182b49b70c57b6 [#43636069] Split gallery actions, change ajax behaviour for links (Manti - Feb 27, 2013)
20 | 45222349 | Fix loader page filling | dev, loader | 7 | 2013-03-11 | 2013-03-17 | bug |  | accepted | 2013-02-27 | 2013-03-11 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/45222349 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/2c989674885fff666ddee2faac99d7bd3d6792b9 [#45222349] Fix loader position (Manti - Feb 27, 2013)
21 | 45302137 | Fix relations control | dev, relations | 7 | 2013-03-11 | 2013-03-17 | bug |  | accepted | 2013-02-28 | 2013-03-11 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/45302137 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/adc1b81077029fe06d96b687fa625ae8865ae05f [#45302137] Fix post relations limit (Manti - Feb 28, 2013)
22 | 45302539 | Fix featured block | dev, featured, markup | 9 | 2013-03-25 | 2013-03-31 | bug |  | accepted | 2013-02-28 | 2013-03-28 |  | Manti | Manti | Check state with one or two items | http://www.pivotaltracker.com/story/show/45302539
23 | 43635923 | Add Google and Yandex analitycs | analitycs, dev, seo | 10 | 2013-04-01 | 2013-04-07 | chore |  | accepted | 2013-02-01 | 2013-04-02 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43635923 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/0eeb2c3a768928f2f31653dda51e85d086c26cfb [#43635923] Add google analitycs (Manti - Apr 2, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/49ba71c3cbf87aaf09b473320416e1fca0bc0a01 [#43635923] Add yandex analitycs (Manti - Apr 2, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/cb884ef9f4b31acbb34a32b3aee117cec5d75601 [#43635923] Add google verification file (Manti - Apr 2, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/6b783e8d8c0d6469c91807a1abd3e4d1d8943411 [#43635923] Add yandex tracker (Manti - Apr 2, 2013)
24 | 43600389 | Create DB copy with "real" contents | copyright | 10 | 2013-04-01 | 2013-04-07 | feature | 2 | accepted | 2013-01-31 | 2013-04-02 |  | Manti | Manti | Copy contents to current system from http://niiar.com | http://www.pivotaltracker.com/story/show/43600389 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/26ea3d2521912b1da20976fd94cdd182468b3b69 [#43600389] Update contents (Manti - Feb 27, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/0ad71346e5f2ef8f441c4620bbe097c63a31de8e [#43600389] Add featured contents (Manti - Feb 28, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/d5eba3719fd8f10f26c697fed53df3b636971d56 [#43600389] Add HOBH series (Manti - Feb 28, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/d9f75876a42e4bf2a227a393ff94fd6f342c7a29 [#43600389] Add copyright, about and other contents (Manti - Feb 28, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/b2ba4d7fffe4adab8c87ee64e6797ad282bf7cd5 [#43600389] Update production DB (Manti - Mar 26, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/a485dd9af3a71de5a316a09e977300f5b9344eb1 [#43600389] Update file dates, minor DB fixes (Manti - Mar 26, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/172d0a246a105c0a3b6d6f4b0293176b31242a6e [#43600389] Update production DB (Manti - Mar 26, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/f177cc4ac9720c3b4defde2f04c1c993bce88ec7 [#43600389] Finish prod DB (Manti - Apr 2, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/23501192a2112b448cd964bc77b67f8575b59fdb [#43600389] Fix tag names (Manti - Apr 2, 2013)
25 | 43635449 | Add search with autocomplete for top input | autocomplete, dev, search | 10 | 2013-04-01 | 2013-04-07 | feature | 0 | accepted | 2013-02-01 | 2013-04-02 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43635449 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/5fcda0d68410b982a87e74ff5e119599b3a79372 [#43635449] Add search in topbar (Manti - Mar 28, 2013)
26 | 45223783 | Fix image key dublicates | dev, images | 10 | 2013-04-01 | 2013-04-07 | bug |  | accepted | 2013-02-27 | 2013-04-02 |  | Manti | Manti | Add error handler fot MySQL error 1062 - dublicate entry | http://www.pivotaltracker.com/story/show/45223783
27 | 45222677 | Create inconset for template | design, icons | 10 | 2013-04-01 | 2013-04-07 | feature | 1 | accepted | 2013-02-27 | 2013-04-02 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/45222677
28 | 45227083 | Check markup in main browsers | browsers, dev, markup | 10 | 2013-04-01 | 2013-04-07 | chore |  | accepted | 2013-02-27 | 2013-04-02 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/45227083
29 | 43635555 | Add tracker for site contents |  | 10 | 2013-04-01 | 2013-04-07 | feature | 3 | accepted | 2013-02-01 | 2013-04-02 |  | Manti | Manti | Need to track next events: 1. Post loaded; 2. Gallery view item; 3. Play preview; 4. Download release. | http://www.pivotaltracker.com/story/show/43635555 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/ac02acd7cb3acdc2e9e0a0e1ea2bfcfd5343c7ac [#43635555] Add tracker for posts (Manti - Feb 6, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/9b32b8efda51d7bc5dd9f00d96d4dd6271112cb2 [#43635555] Add tracker for gallery and other files (Manti - Feb 10, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/98e3b5a66a2e0e6b2d57922be2465f8f2978cf2b [#43635555] Replace gallery tracker with ID (Manti - Feb 10, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/6e20ebb9be12b6f4ffe8856ca16485f6bd0db4e7 [#43635555] Add tracker for full gallery view (Manti - Feb 11, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/b9a21dc3d267f3dd7f6bf25794f45af8a44086a5 [#43635555] Add track action for preview (Manti - Apr 12, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/c54bd6dc91f675d6f044169943bfa3188184b988 [#43635555] Add rel ID for audio tag (Manti - Apr 12, 2013) | [6 empty] | Post loaded | completed | Gallery view item | completed | Play preview | completed | Download release | completed | Full gallery view | completed
30 | 43765847 | Redesign covers | covers, design | 11 | 2013-04-08 | 2013-04-14 | chore |  | accepted | 2013-02-04 | 2013-04-09 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43765847
31 | 44191077 | Add try/catch blocks for FS actions | dev, filesystem | 11 | 2013-04-08 | 2013-04-14 | feature | 1 | accepted | 2013-02-11 | 2013-04-09 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/44191077
32 | 43634591 | Add page metakey agregator |  | 11 | 2013-04-08 | 2013-04-14 | feature | 2 | accepted | 2013-02-01 | 2013-04-10 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43634591 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/51c657197aa90e69695db46dc71f16cdf9a745f6 [#43634591] Add cap text for meta info (Manti - Apr 2, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/28dc115d3d7ba54caff7efcac97886e7cd72208e [#43634591] Add page metakey agregator (Manti - Apr 10, 2013)
33 | 43599603 | Create favicon for site | design | 12 | 2013-04-15 | 2013-04-21 | feature | 0 | accepted | 2013-01-31 | 2013-04-16 |  | Manti | Manti | Need to create 3 icons related to the site design and logo: 16x16, 32x32, 64x64. | http://www.pivotaltracker.com/story/show/43599603
34 | 43599459 | Create logo for site | design | 12 | 2013-04-15 | 2013-04-21 | feature | 1 | accepted | 2013-01-31 | 2013-04-16 |  | Manti | Manti | Need to create site logo related to current site (http://niiar.com) style. Please check design of all cover images for mixes on this site. Also you can use names of these mixes as tags and ideas. Other social resource: http://promodj.com/manti.by | http://www.pivotaltracker.com/story/show/43599459 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/07a939ea64553c98c410c114582eb12f75639d48 [#43599459] Add logo spec (Manti - Feb 1, 2013) | (Manti - Feb 1, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/d3c07b192426f931a6d3e5f35e380cfb9c089f54 [#43599459] Update logo specs (Manti - Feb 7, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/aa2404f441f4953f619ecaea58ac495b63d1aa0d [#43599459] Add site logo (Manti - Apr 16, 2013)
35 | 43637897 | Add error markup for all ajax messages | dev, markup | 12 | 2013-04-15 | 2013-04-21 | chore |  | accepted | 2013-02-01 | 2013-04-16 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43637897 | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/a9e612e406976625f0320fd94257d8a30fe80722 [#43637897] Fix ajax messages (Manti - Apr 16, 2013)
36 | 43635731 | Create semantic core for site | seo, tags | 17 | 2013-05-20 | 2013-05-26 | chore |  | accepted | 2013-02-01 | 2013-05-24 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43635731
37 | 50253649 | Add watermark to gallery images |  | 17 | 2013-05-20 | 2013-05-26 | feature | 2 | accepted | 2013-05-21 | 2013-05-24 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/50253649 | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/7835a752d19f61fc04c3b1600f319993d5432b33 [#50253649] Add watermark for gallery originals (Manti - May 24, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/f397311929d77ec23601b31cb0312547a904017e [#50253649] Add headers for watermarked images (Manti - May 29, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/94e39c5f92957830185dbe9cdb61d81e24ff41b6 [#50253649] Fix expires (Manti - May 29, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/d83cb36eeefdc39f3a1c93206c912d30fb0783b8 [#50253649] Fix mime type (Manti - May 29, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/047171f4adb18499912a1a3ce4d9be0f1d34dbc8 [#50253649] Fix expires date format, update htaccess (Manti - May 29, 2013)
38 | 50253637 | Fix 404 page responce in sef |  | 18 | 2013-05-27 | 2013-06-02 | bug |  | accepted | 2013-05-21 | 2013-05-28 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/50253637 | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/1ec1fd8443b50c11c0f923246a8bfc50a042c7d6 [#50253637] Fix 404 page (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/946ffa603011eb50441511a2f76553e456cac9af [#50253637] Add simple test for sef convert (Manti - May 28, 2013)
39 | 50639317 | Convert markup to valid W3C |  | 18 | 2013-05-27 | 2013-06-02 | bug |  | accepted | 2013-05-28 | 2013-05-28 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/50639317 | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/979333e70aa17f5db39898375e9511ffaf827006 [#50639317] Fix filelist markup (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/320caac343330c688a5ccc80349b0140097c90af [#50639317] Fix search input markup (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/d5bf8d43ffd4f6a4254d57dc5d1313a9dd420b4e [#50639317] Fix rel attribute, fix trackers (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/58b68b4c0760949a3f6b02e5fd2640e4b8e2a291 [#50639317] Fix rel attribute in gallery (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/19c5841273ca073b3b631e71f7ddb5b6fb39eedd [#50639317] Fix header links (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/83e715c4fe10d610200fcd9fc9b754a51cc4b19a [#50639317] Fix gallery anchors (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/9885d60224dd1f8c0bb5f50028d990aa38bfbe07 [#50639317] Fix image anchors (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/984c7dd52cbc36c9f659711783634ca75ab6f59c [#50639317] Fix file table width (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/240f0f1d6f931334141fea5311d8140d7dfd9d84 [#50639317] Update robots file (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/d4ab80cf3bc903ed872c04d964dd14fd8f3dc012 [#50639317] Update 404 behaviour (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/17a30e50a7387e25273a79d498dff3d23c095937 [#50639317] Fix 404 redirect (Manti - May 28, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/a71040906bd094305765236db563c6c1d985cf3b [#50639317] Merge w3c changes (Manti - May 29, 2013)
40 | 50516379 | Fix nginx watermark redirect |  | 18 | 2013-05-27 | 2013-06-02 | bug |  | accepted | 2013-05-24 | 2013-05-29 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/50516379 | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/2cc1efc0fe88303d2134d26e9f6c1b47004b2da9 [#50516379] Add watermark file (Manti - May 29, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/8b9618fb9ed62283d7825b0d98493b6c40d962e5 [#50516379] Fix redirect (Manti - May 29, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/668c2b405316a9026ff4925ef511f42164331c70 [#50516379] Fix file path (Manti - May 29, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/d7a6c2597125f822c4cb8fd7e32038a376c0c595 [#50516379] Fix file path in model (Manti - May 29, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/a5af3ac4e1783fee29e17f0f7a74b9dbecfad9f3 [#50516379] Minor fix (Manti - May 29, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/1e76ce0fce00837b4af7fa98670c113bd40ca619 [#50516379] Complete watermarks (Manti - May 29, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/666b3da48ce6a8b3236ae64ce589aebff616a47a [#50516379] Update production config (Manti - May 29, 2013)
41 | 50512523 | Add printable version of blog posts |  | 18 | 2013-05-27 | 2013-06-02 | feature | 2 | accepted | 2013-05-24 | 2013-05-29 |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/50512523 | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/0aed52f93101a9dc4ee8f545bfa9dd2b7dd21d4d [#50512523] Add printable blog post (Manti - May 29, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/e4d33213f0919dd21f4e5dc5cae36077eb110d19 [#50512523] Add print media css (Manti - May 29, 2013)
42 | 49746633 | Content player | dev, player | 18 | 2013-05-27 | 2013-06-02 | feature | 3 | started | 2013-05-13 |  |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/49746633 | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/8a51336cc9f53ebee9239b847db997aaa5bf71fe [#49746633] Add inline player (Manti - May 15, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/6cd7ac9a91d78293ae0d079878f3d4f5bccf694b [#49746633] Update design for player, logo, favicon (Manti - May 30, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/56526c376f17cfe63a5b1db2b555c156bafe8154 [#49746633] Minor fixes (Manti - May 30, 2013) | Commit by marco-manti https://github.com/manti-by/M2_micro/commit/ceb1ee8cde9223f6cb1106b1fd1af8299db4ef51 [#49746633] Update design, new animated favicon (Manti - May 31, 2013)
43 | 44528397 | Utilites development | core, dev, utils | 18 | 2013-05-27 | 2013-06-02 | chore |  | started | 2013-02-15 |  |  | Manti |  |  | http://www.pivotaltracker.com/story/show/44528397 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/10eeaadc7374197f529fce4e587cb4b3694abf07 [#44528397] Add rollback action to DMB (Manti - Feb 15, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/645849b04a1e0a47b1a175f9a236ed89ba79eead [#44528397] Add remigrate action, change tool structure (Manti - Feb 15, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/95aa9a4d968d0aa3f298dafcf792d227c27d8a95 [#44528397] Fix rollback depth for DBM (Manti - Feb 15, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/938f833b929ec731e1e499426d2762f270c636f1 [#44528397] Update DBM version (Manti - Feb 15, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/c2a78bc50e7cd16a163817c2c67904ab85a22a17 [#44528397] Fix comment length (Manti - Feb 27, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/e9cac99d71328a46048f3d0f99f8dade6ecab558 [#44528397] Move PHP metric runners to utils (Manti - Feb 27, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/ab8e402fdc85b3eeb6835184339dff0309095247 [#44528397] Update phpDoc and phpDepend (Manti - Apr 9, 2013) | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/242f59417502ca4fb3bc1a1e4a7cbafb044c3da7 [#44528397] Add comments remover (Manti - Apr 9, 2013)
44 | 43628887 | Create social plugins | dev, social, vk | 18 | 2013-05-27 | 2013-06-02 | feature | 2 | started | 2013-02-01 |  |  | Manti | Manti | Need to aad ability post site blog posts directly to owner http://vk.com wall. Plugin should support audio and video attachments. | http://www.pivotaltracker.com/story/show/43628887
45 | 43600295 | Add ACL check on SEF init | acl, dev | 20 | 2013-06-10 | 2013-06-16 | feature | 2 | unstarted | 2013-01-31 |  |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43600295 | [12 empty] | Check user login | not completed
46 | 44191007 | Fix collation on CHECK_COOKIE | database, dev | 20 | 2013-06-10 | 2013-06-16 | bug |  | unstarted | 2013-02-11 |  |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/44191007
47 | 45218979 | Fix file list population | dev, files | 20 | 2013-06-10 | 2013-06-16 | bug |  | unstarted | 2013-02-27 |  |  | Manti | Manti | Add multiple types in GET_FILES(...) | http://www.pivotaltracker.com/story/show/45218979 | Commit by marco-manti https://github.com/marco-manti/M2_micro/commit/670696331981dca293e76795b50cf448e25a9c1f [#45218979] Fix limit size (Manti - Feb 27, 2013)
48 | 45219467 | Fix click on popup content | dev, popup | 20 | 2013-06-10 | 2013-06-16 | chore |  | unstarted | 2013-02-27 |  |  | Manti | Manti | http://stackoverflow.com/questions/2457246/jquery-click-function-exclude-children | http://www.pivotaltracker.com/story/show/45219467
49 | 49747115 | Add nginx counters merging for OGG files | dev, nginx, stats |  |  |  | feature | 1 | unscheduled | 2013-05-13 |  |  | Manti |  |  | http://www.pivotaltracker.com/story/show/49747115
50 | 44195055 | Need code refactoring to standartize get / by id / by tags actions | blog, core, dev, gallery |  |  |  | feature | 2 | unscheduled | 2013-02-11 |  |  | Manti | Manti | Refactor code in blog and gallery | http://www.pivotaltracker.com/story/show/44195055
51 | 43635429 | Add comments plugin for whole site | comments, dev |  |  |  | chore |  | unscheduled | 2013-02-01 |  |  | Manti | Manti |  | http://www.pivotaltracker.com/story/show/43635429